## 8D report
Plan for 8D report |  |  | Complaint no. (Customer):
Complaint no. (Supplier):
Revision:
Response Due Date:
Progress | 1D | 2D | 3D | 4D | 5D | 6D | 7D | 8D
Action | Establish team | Define problem | Contain-ment Action | Find root cause | Corrective action | Validate corrective actions | Preventive actions | Sign off & celebrate
Due date
Actual date
Customer complaint information
Case title:
Customer: | Response Due Date: 4D: Date notificated:
Customer part no.: | Response Due Date: 4D: Supplier part no.:
Part name: | Response Due Date: 4D: Decision:
Complaint quantity: | Response Due Date: 4D: Supplier serial no.:
Delivered quantity:
Customer order no.: | Response Due Date: 4D: Supplier order no.:
Customer return order no.: | Response Due Date: 4D: Supplier return order no.:
Finding area: | Response Due Date: 4D: Finding severity:
Finding classification: | Response Due Date: 4D: Customer request:
Other products/processes concerned?
Does the problem represent a safety issue?
Does the problem represent a environmental issue?
How was the finding discovered?
What kind of finding:
1D - Establish Team - Establish a small group of people with the process/product knowledge, allocated time, authority and skill in the required technical disciplines to solve the problem and implement corrective actions.
Name | 2D: Department; Response Due Date: 4D: Team Function; Response Due Date: 6D: Responsibility
2D - Define problem
| IS |  |  |  | IS NOT
Who | 1D: Who is affected by the problem? Who did first observe the problem? To whom was the problem reported?; Response Due Date: 5D: Who is not affected by this problem? Who did not find the problem?
When | 1D: When was the problem fisrt notices? When has it been noticed since?; Response Due Date: 5D: When could the problem have been noticed but was not ?
Where | 1D: Where was the problem observed? Where does the problem occur?; Response Due Date: 5D: Where could it be located but is not?
Why | 1D: Why is this a problem? Is the process where the problem occurs/occurred stable?; Response Due Date: 5D: Why is it not a problem?
What | 1D: What type of problem is it? What is happening?; Response Due Date: 5D: What does not have the problem? What could be happening but is not ? What could be the problem but is not?
How often | 1D: What is the trend? (continuous, random, cyclical); Response Due Date: 5D: What could be the trend but is not?
How many | 1D: Quantity of problem?; Response Due Date: 5D: How many could have the problem but don´t?
2D - Define problem - Continue
Description of Problem - Customer view
Potential Causes (Sketch or Photo of the problem can be added in appendix)
3D - Define and implement containment action (Use Compilation of deliveries-tab)
Containment needed?
What |  | Do it | How (containment action) |  |  | Who | When | How many
Need to check own stock
Need to check supplier stock
Need to check customer stock
Immediate action at customer
4D - Find root cause
Root cause for Occurrence (Use 5 Why-tab or Fishbone-tab)
Root cause for Non Detection
Action Plan - Based on the team’s discussions. Begin to complete the Root Cause Action Plan to verify and validate the root causes and test the escape point. Document this on the Action Item Table.
Likely root cause: Effect: Recommendation: Level for Action: Implementation: Evidence: Target Date:
No failure discovered - Product fully functional
5D - Define and implement corrective actions
Permanent Corrective action for Occurrence
All permanent corrective action for Occurrence implementation date
Permanent Corrective action for NON Detection
All permanent corrective action for NON Detection implementation date
6D - Validate corrective action
Method of Validation (eg. Audit, KPI) | Response Due Date: 4D: Validated OK/NOK; Response Due Date: 5D: Who; Response Due Date: 7D: Due date; Response Due Date: 8D: Actual date
Effectiveness implementation date
7D - Define and implement preventive action
Once corrective actions have been verified and proven effective, those actions must be standardized to relevant products/processes to prevent the same failure in the future
Preventive actions | Response Due Date: 4D: Where; Response Due Date: 5D: Who; Response Due Date: 7D: Due date; Response Due Date: 8D: Actual date
Need to update FMEA | Response Due Date: 3D: Following FMEAs are updated, Date
Are there any Lesson Learned card | Response Due Date: 3D: Following LLC are made, date
7D - Review of documents
Document including document number (Management System Manual, Manufacturing Work Instructions, Inspection Work Instructions, Flow Charts, Control Plans, Gauges, PPAP, Engineering Change Notices, ISIR/FAI, Contract Review) | Response Due Date: 4D: Applicable; Response Due Date: 5D: Responsible; Response Due Date: 7D: Planned due date; Response Due Date: 8D: Actual due date
8D - Sign off & celebrate
Celebrate success and identify lessons learned
Responsible | Response Due Date: 3D: Planned due date; Response Due Date: 6D: Actual due date
Appendix
2D - Define problem In this step it is important to clarify the issue type, what is wrong, when did it happen, how big the failure extent is and how many times has it happened. The questions asked in this step is to help you clarify the issue. The 8D method’s initial focus is to properly describe the problem utilizing the known data and placing it into specific categories for future comparisons. The “Is” data supports the facts whereas the “Is Not” data does not. As the “Is Not” data is collected, many possible reasons for failure are able to be eliminated.
3D - Define and implement containment action In this step we try to limit the problem extent and protect our customer. Containment actions are a “first aid” that protects the customer from the problem until we define the root cause and implement permanent corrective actions. Once the problem is described, before heading up to problem solving, the team should fix the effect of the problem, especially on customers. It might involve actions like isolating the items affected, replacing defective parts, before it reaches the customers. This step is mainly to prevent the problem from reaching the market and customers, which might become a competitive disadvantage and reduce customer loyalty.
4D - Find root cause To effectively prevent a problem from occurring again we have to find the root cause of this problem and remove it. In rare situations there could be more than one root cause. To identify the root cause, a systematic and well-documented analysis is needed. Each possible cause should be tested against the problem description and test data. Root cause is often hidden by other causes and can be hard to find. There are many methods that can be used during the analysis. For example, is/is not, 5 Whys, Ishikawa Fishbone and others. See exampels of 5 Why´s in tab "5 Why" Root cause for Non Detection Which is the closest point in the process where the root cause could have been found but was not.
Why was the problem not detected before delivery or in production or during the development phase? - Which possible factors have ypu detected in the IS/IS NOT analysis? - Compare to the standard, verify the standard. - Validate the identified factors e.g. reproducing the non-conformity or dismiss the factor. - Take the validated factors and use 5 Why´s to drill down into management and organizational root cause NOTE: If root cause analysis results in no complaint due to no fault found or customer fault it should clearly be stated in this step. The 8D-report should be complete from step 1D to 4D and then sent to BAESH for discussion and approval.
5D - Define and implement corrective action The goal of corrective actions is to remove the root cause and prevent the problem from ever happening again. If good corrective actions have been taken we should never have to write another 8D report for this problem. In this step we are concentrated on a specific event or problem that has already arisen.
The corrective actions have to be carefully documented. For each action a responsible person should be identified and the date when the action is planned to be implemented should be selected. When an action has been finished the actual date of implementation and results should be recorded.
For each root cause identified there are usually many corrective actions needed.
6D- Validate corrective action The purpose of this 8D Report step is to verify if the actions taken in step 5D have removed the root cause. If we discover that the root cause has not been completely removed, then we have to point out additional measures. It is sometimes necessary to return to root cause analysis in step 4D and repeat the cycle.
7D - Define and implement preventive action At first glance this step is very similar to step 5D . The difference between these two steps in 8D Report is in the reason why we perform them and in final goal. Actions in step 5D are meant to prevent an existing problem from happening again. In contrast, preventive actions remove causes for a potential problem and prevent it from ever happening. 7D actions are proactive and oriented towards a potential event in the future.
Actions are usually based on results of FMEA analysis or observations of negative trends. Often, concrete problems encourage us to think about other problems that could arise on the same product or about the same problem arising on another product or process.
Overall instruction 8D process and 8D report 8D methodology uses a structured eight step approach to problem solving. The objective is to face the problem and discover the weaknesses in the management systems that permitted the problem to occur in the first place. The output of an 8D process is an 8D report.
1D - Establish Team The approach is based on a team working together to solve a problem. Teamwork must be coordinated and guided. The team should include only competent persons actively involved in the process and who have been assigned a task or responsibility in subsequent steps.
Customer complaint information Fill in as much information as possible and ask the customer for additional information if needed.
Plan for 8D report Plan for solving the problem and determine the prerequisites.
8D - Sign off & celebrate At the end of an 8D process is the time to recognize the team efforts and special team member contributions. This is also a good point to document lessons learned.

## Compilation of deliveries
Compilation of deliveries
Customer PO | Supplier Invoice | Date | Batch | Quantity | Return Date (Supplier) | Return Ref (Q-notification no.) | NCR Ref (Supplier no.) | Return Quantity | Miscellaneous

## 5 Why
5 Why | Example 5 Why
Potential Cause | Potential Cause | One of five screws to a bracket was not tightened to the correct torque
1st Why | 1st Why | Why were not all five screws tightened to the correct torque? The operator failed to tighten the fifth screw.
2nd Why | 2nd Why | Why could the torque of the fifth screw be overlooked? Because the operator was interrupted by a colleague during the installation.
3rd Why | 3rd Why | Why did the interuption cause the torque of the fifth screw to be ignored? It was unclear to the operator which screws were tightened.
4th Why | 4th Why | Why was it unclear to the operator which screws were tightened? All the screws were screwed to the bottom by hand so that they looked tight.
5th Why | 5th Why | Why were all the screws screwed to the bottom so that they looked tight? For the method standard says that all the screws must be ignited and screwed to the bottom by hand before using torque wrenches.
5 Why |  | Root cause: A defect in the method standard. Short-term solution: Possible solution so that the problem does not occur again: Change the method standard so that each screw is tightened immediately after entering so that it becomes visual which screws are tightened. Long-term solution: See if there are more products where this step exists. If yes, change these method standards as well for these products.
Potential Cause
1st Why
2nd Why
3rd Why
4th Why
5th Why
5 Why
Potential Cause
1st Why
2nd Why
3rd Why
4th Why
5th Why
5 Why
Potential Cause
1st Why
2nd Why
3rd Why
4th Why
5th Why

## Fishbone
Fishbone
Problem description:
Parameters | Factors | Potential Root Cause (If there is a direct link)

## Action list
Action list
Actions |  |  | Implement and Verify actions
Action # | Fault/Item | Containment/ Corrective Actions | Verify | How verified | Action | Accountability | Planned | Actual | Status
1
2
3
4
5
6
7
8
9
10

## Drop list (do not change)
Finding area | Health and safety
Enviroment
Quality
Others
|  | Yes | Yes | Fisk | Method
|  | No | No |  | Material
Decision: | Warranty | Don't know |  |  | Man
| Godwill |  |  |  | Machines
Management
Recipient (Customer)
Finding classification | Major Non-conformity | Finding severity | Accident |  | Customer sales request | 8D Report
| Minor Non conformity |  | Near Miss |  |  | Failure Analysis Report
| Observation |  | Operations |  |  | No Preference
| Improvement |  | Complaint |  |  | Other
How was the finding discovered | Internal Audit finding
What kind of finding | External Audit finding
Customer Audit finding
Internal operational finding
Customer finding
Other…