## Checklist
First Piece / First Article Checklist
Critera |  |  |  | Please note: Each of these categories to have the same TABs for ALL assemblies or components
Accept | Reject | N/A | Number | Revision | BINDER TABs
1. Top Assembly Part number - per PO
A. Purchase Order
B. Ballooned drawing (all dimensions and notes)
C. Full dimensional inspection report including actual data for all variable dimensions including drawing notes as applicable - note: C=0 sampling
i. Measuring equipment and calibrations to be verified
D. Material Certifications
i Ballistic Firing Record / thermally cut edges (process approval)
E. Finish / Paint Certifications (Approved Supplier for CARC)
F. Non-destructive testing data/certification
G. Performance Testing data/certification
H. Part marking per PO but use drawing for location and cage code
J. Weld (WPS), Certification
K. DFARs compliant - no parts from Asia, especially bearings - SQAM 6.5
L. Special Processes - use of approved suppliers - SQAM 7.0
i.. Inspection documentation for painted parts - per SQAM 7.1.2.1
M. Non-Conforming Material -attach approved waiver, must have BAE buyer and Engineering approval and attached to PO per SQAM 8.6
N. Packaging - per SQAM 9.0 and any PO requirements
O. Age Sensitive Materials - per SQAM 9.4
P. GSI required, verify signature affixed to documentation
Q. CSI required, assure review and approval, verify Source Approval form completed/attached
R. Other CDR requirements assigned per the purchase order
Accept | Reject | N/A | Number | Revision | BINDER TABs
1. Component Part number
A. Purchase Order
B. Ballooned drawing (all dimensions and notes)
C. Full dimensional inspection report including actual data for all variable dimensions including drawing notes as applicable - note: C=0 sampling
i. Measuring equipment and calibrations to be verified
D. Material Certifications
i Ballistic Firing Record / thermally cut edges (process approval)
E. Finish / Paint Certifications (Approved Supplier for CARC)
F. Non-destructive testing data/certification
G. Performance Testing data/certification
H. Part marking per PO but use drawing for location and cage code
J. Weld (WPS), Certification
K. DFARs compliant - no parts from Asia, especially bearings - SQAM 6.5
L. Special Processes - use of approved suppliers - SQAM 7.0
i.. Inspection documentation for painted parts - per SQAM 7.1.2.1
M. Non-Conforming Material -attach approved waiver, must have BAE buyer and Engineering approval and attached to PO per SQAM 8.6
N. Packaging - per SQAM 9.0 and any PO requirements
O. Age Sensitive Materials - per SQAM 9.4
P. GSI required, verify eagle stamp affixed to documentation
Q. CSI required, assure review and approval, verify Source Approval form completed/attached
R. Other CDR requirements assigned per the purchase order
Accept | Reject | N/A | Number | Revision | BINDER TABs
1. Component Part number
A. Purchase Order
B. Ballooned drawing (all dimensions and notes)
C. Full dimensional inspection report including actual data for all variable dimensions including drawing notes as applicable - note: C=0 sampling
i. Measuring equipment and calibrations to be verified
D. Material Certifications
i Ballistic Firing Record / thermally cut edges (process approval)
E. Finish / Paint Certifications (Approved Supplier for CARC)
F. Non-destructive testing data/certification
G. Performance Testing data/certification
H. Part marking per PO but use drawing for location and cage code
J. Weld (WPS), Certification
K. DFARs compliant - no parts from Asia, especially bearings - SQAM 6.5
L. Special Processes - use of approved suppliers - SQAM 7.0
i.. Inspection documentation for painted parts - per SQAM 7.1.2.1
M. Non-Conforming Material -attach approved waiver, must have BAE buyer and Engineering approval and attached to PO per SQAM 8.6
N. Packaging - per SQAM 9.0 and any PO requirements
O. Age Sensitive Materials - per SQAM 9.4
P. GSI required, verify eagle stamp affixed to documentation
Q. CSI required, assure review and approval, verify Source Approval form completed/attached
R. Other CDR requirements assigned per the purchase order
Accept | Reject | N/A | Number | Revision | BINDER TABs
1. Component Part number
A. Purchase Order
B. Ballooned drawing (all dimensions and notes)
C. Full dimensional inspection report including actual data for all variable dimensions including drawing notes as applicable - note: C=0 sampling
i. Measuring equipment and calibrations to be verified
D. Material Certifications
i Ballistic Firing Record / thermally cut edges (process approval)
E. Finish / Paint Certifications (Approved Supplier for CARC)
F. Non-destructive testing data/certification
G. Performance Testing data/certification
H. Part marking per PO but use drawing for location and cage code
J. Weld (WPS), Certification
K. DFARs compliant - no parts from Asia, especially bearings - SQAM 6.5
L. Special Processes - use of approved suppliers - SQAM 7.0
i.. Inspection documentation for painted parts - per SQAM 7.1.2.1
M. Non-Conforming Material -attach approved waiver, must have BAE buyer and Engineering approval and attached to PO per SQAM 8.6
N. Packaging - per SQAM 9.0 and any PO requirements
O. Age Sensitive Materials - per SQAM 9.4
P. GSI required, verify eagle stamp affixed to documentation
Q. CSI required, assure review and approval, verify Source Approval form completed/attached
R. Other CDR requirements assigned per the purchase order

## Work Instruction
First Piece / First Article Checklist Instruction
The purpose of this work instruction is to guide the Supplier and BAE Systems in conducting a First Article Inspection (FAI) or First Piece review.
The scope of this work instruction applies to parts made by suppliers for FAI requirements as defined in the PO or Technical Data Package as well as first piece per SQAM paragraph 8.3.
2.0 INSTRUCTION DETAILS
a. Identify and attach a copy of the purchase order.
b. Pull PO from Oracle and print:
o Go to the lines and then attachments and verify the CDR requirements and drawings on the configuration sheet.
o Note the drawing revision(s).
o Review PO revision history. Note any additional changes or requirements.
c. Starting with the drawing at the revision level listed in the PO:
o Ensure all drawing notes and dimensions are ballooned.
o Review each balloon number on the drawing and ask for the objective evidence:
§ A general statement from a supplier is not considered evidence.
§ A Certificate of Conformance (C of C) does not constitute evidence.
§ Actual results must be listed on the objective evidence.
o If the note on the drawing states a specification, then the results shall contain the specification number and revision.
o Dimensions are required for all balloons on the drawing as well.
§ Gages used to inspect the dimensions are required to be identified – e.g. CMM, calipers, etc.
§ Verify gages used are calibrated and within the calibration date on the sticker on the gage.
o Verify material certifications meet DFARs – no materials made or manufactured in non-qualifying countries.
o Verify part marking per the drawing – NOTE: the drawing calls out the cage code and location, unless otherwise stipulated on the purchase order. The part number to be used is the part number listed (item number) on the PO.
o Verify packaging.
o Verify visually parts are not corroded, rusted, carbon deposited, weld splatter, other detrimental appearance or contamination.
o Verify all special processes are using the required suppliers or are approved by BAE – e.g. Weld approval is required and use of an approved painter.
o Age sensitive materials meet the SQAM / CDR Requirements.
o No HAND written changes to the contract are allowed.
o Use 1st piece checklist # (need the BMS Number listed here) to ensure all parts / components have been verified.
d. Repeat all of the steps in 2.0 for all components in the assembly (Each component will be recorded in separate binder tabs).
e. Review the part to ensure it meets the requirements for:
o CARC painting – painter is listed as per SQAM requirements.
o Quantities of components are correct.
o Verify components meet the drawing for specification used and color.
f. For any component or assembly that does not meet the above requirements, PO, or drawing must have a SIGNED document from BAE Buyer to allow the use of the parts for the reasons listed as discrepant.
o Note: Acceptance criteria is C=0 – no defects.
g. All BAE SQAM and CDR requirements must be met.
h. All documents and objective evidence must be placed in a file/binder/folder and identified by the BAE part number listed on the purchase order. Each part number and subcomponent must have its own section/tab in the file.
3.0 RECORD RETENTION
Records shall be managed in accordance to the ISO 9001 Quality Management Systems Requirements, clause 4.2.4 Control of Records, the BAE Systems, Inc. Record Management Policy 218 and U.S. Records Retention Schedule.
4.0 DEFINITIONS
1. SQAM – Supplier Quality Assurance Manual
2. PO – Purchase Order
3. C of C – Certificate of Conformance
4. FAI / 1st pc – First article inspection / 1st piece
5. CDR – Contract Deliverables Requirements
6. TDP – Technical Data package
6.0 REVISION HISTORY
Rev | Date | Change Description | Approved By | Change Request #
- | 2016-04-21 | Initial Release | Tom Frazho/Anthony Conely | BPMS-02870